## Sheet1
1. Education : Implementing a Student Data Management System for
CSUEB Admissions Department
Industry: Education
● Project Example: Implementing a Student Data Management System to handle
admissions-related data at Cal State East Bay, including student applications, | Transform data in two phases
transcripts, enrollment, and admission decisions.
● Scope: Define system infrastructure requirements, train admissions staff, migrate
student application and admissions data from legacy systems, and ensure compliance
with student data privacy regulations.
● Milestones: Needs assessment, infrastructure setup, vendor selection, data migration,
pilot testing, and full implementation.
● Agile Application: You can implement the system in phases, starting with current
students data and gradually expanding it to historical records.
Why it's of our interest: This project ensures efficient and compliant admissions data
management, streamlining the application process and maintaining compliance. It also offers
insights into handling large volumes of sensitive data and applying Agile methodologies for
system rollouts in education.

## Structure
LEVEL 1 | California State University East Bay
Admission Department ¦ Migrating the server date (Student Data) to the cloud
| Hayward |  |  |  | Oakland |  |  |  | Concord
[5 empty] | N/A, refer to Continuing Education |  |  |  | Undergraduate: Nursing, Psychology
| College and Deparment | [7 empty] | Certificate in Paralegal Studies
Teaching Credential - Single and multiple subjects
|  | Graduate Program | Undergraduate Program
| College of Business and Economics | M.B.A. | B.S in Business Adminsitration
|  | Ms in Accountancy | B.S. in Accounting and Analytics
|  | Ms in Business Analytics | B.S. in Business Analytics
|  | Ms in Marketing Analytics | B.S. in Economics
| College of Education and Allied Studies | M.S. In Education | B.S. In Hospitality and Tourism
|  | M.S. In Educational Leadership | B.S. In Recreation
|  | M.S. in Educational Technology | B.S. In Kinesiology
M.S. in Curriculum and instruction
M.S. in Reading
M.S. in eLearning (Online)
M.S. in Hospitality, Recreation and Tourism (Online)
M.S. In Kinesiology
M.S. In Counseling
M.S. In Special Education
| College of Letters, Arts and Social Science | Communication, M.A. | Liberal Studies, B.A.
|  | English, M.A. | Music, B.A.
|  | History, M.A. | Spanish, B.A.
|  | Interaction Design and Interactive Art, M.A. | Speech Pathology and Audiology, B.S.
|  | Music, M.A. | Theatre Arts, B.A.
|  | Public Administration, M.P.A. | Philosophy, B.A.
Political Science, B.A.
Sociology, B.A.
Anthropology, B.A.
Art, B.A.
Art, B.F.A.
Communication, B.A.
Criminal Justice, B.S.
English, B.A.
Environmental Studies, B.A.
Ethnic Studies, B.A.
French, B.A.
Geography, B.S.
Global Studies, B.A.
History, B.A.
Human Development, B.A.
| College of Science | Biological Science, M.S. | Biochemistry, B.A.
|  | Biostatistics, M.S. | Biochemistry, B.S.
|  | Chemistry, M.S. | Biological Science, B.A.
|  | Computer Science, M.S. | Biological Science, B.S.
|  | Construction Management, M.S. | Chemistry, B.A.
|  | Engineering Management, M.S. | Chemistry, B.S.
|  | Environmental Geosciences, M.S. | Civil Engineering, B.S.
|  | Health Care Administration, M.S. | Computer Engineering, B.S.
|  | Marine Science, M.S. | Computer Science, B.S.
|  | Mathematics, M.S. | Construction Management, B.S.
|  | Nursing, M.S. | Environmental Science, B.S.
|  | Quantitative Economics, M.S. | Geology, B.A.
|  | Social Work, M.S.W. | Geology, B.S.
|  | Statistics, M.S. | Health Sciences, B.S.
Industrial Engineering, B.S.
Mathematics, B.S.
Nursing*, B.S.
Physics, B.A.
Physics, B.S.
Psychology, B.S.
Statistics, B.S.
| Continuing Education | Behavioral and Health Sciences: Hybrid Master of Science in Nursing Pre-Professional Health Academic Program Certificate in Addiction Studies Certificate in Pharmacy Technician Equivalency Path Program in Recreation Therapy Speech-Language Pathology Assistant Program Trauma Informed Specialist Program | Business and Management: Online BS in Business Administration (BSBA) Certificate in Ethical AI in Business and Leadership Certificate in Human Resource Management Certificate in Nonprofit Management Certificate in Payroll Practice and Management Certificate in Project Management | Cannabis Studies: Certificate in Cannabis Healthcare and Medicine Certificate in Cannabis Agriculture and Horticulture Certificate in The Business of Cannabis Certificate in Cannabis Compliance and Risk Management | Construction and Sustainability: Certificate in Construction Management | Continuing Education for Licensure: California State Notary Public Training Teacher Education Minimum Continuing Legal Education (MCLE) | Corporate Training: Conference Facilities | Cyber Security: Cyber Bootcamp | Education: Certificates in eLearning Online MS in Educational Leadership Online MS in eLearning Online MS in Reading and Literacy Online Single Subject Teaching Credential Teacher Education Trauma Informed Specialist Program | Engineering and Project Management: Certificate in Project Management | Health Care: Hybrid Master of Science in Nursing Pre-Professional Health Academic Program Equivalency Path Program in Recreation Therapy | Hospitality: Hospitality, Recreation, and Tourism Certificates | Legal Studies: Certificate in Paralegal Studies Minimum Continuing Legal Education (MCLE) California State Notary Public Training | Medical: Pre-Professional Health Academic Program Certificate in EKG Technician Certificate in Medical Billing and Coding Hybrid Master of Science in Nursing Certificate in Pharmacy Technician | Sport Performance: Sport Performance Program Expanded Collection | Tech Bootcamps: Coding Bootcamp Cyber Bootcamp Product Management | Transportation: Certificate in Freight Broker/Agent Training | Veterinary: Certificate in Veterinary Assistant

## Sheet3
Project Description
This project focuses on migrating from an existing Student Data Management System to a new, more efficient platform to handle admissions-related data at California State University, East Bay (CSUEB). The current system has limitations in managing student applications, transcripts, enrollment, and admission decisions, which necessitates the transition to a more robust solution.
The new system aims to:
Enhance Data Management: Improve the management of student applications, ensuring seamless processing and retrieval of information.
Streamline Processes: Automate workflows for admission decisions and enrollment processes to reduce manual work and increase efficiency.
Upgrade Technology Infrastructure: Transition to a cloud-based platform that offers greater flexibility, scalability, and security in handling sensitive student data.
Ensure Compliance: Adhere to the latest data privacy regulations and standards, safeguarding student information throughout the migration process.
Integrate with Other Systems: Ensure compatibility and integration with other university systems (e.g., financial aid, student records) to create a cohesive user experience.
Migration Scope
Data Migration: Transfer all relevant student admissions data, including applications, transcripts, and historical data from the legacy system to the new platform.
System Integration: Ensure that the new system integrates effectively with existing systems at CSUEB to maintain operational continuity.
Training: Provide comprehensive training for admissions staff on the new system to ensure a smooth transition and minimize disruption to the admissions process.
Testing: Conduct thorough testing of the new system to verify that all data has been accurately migrated and that processes function as intended.
Monitoring: After implementation, monitor system performance and user feedback to address any issues promptly and ensure the system meets the needs of the admissions department.
Milestones
Needs Assessment: Evaluate the current system’s limitations and identify requirements for the new system.
Vendor Selection: Research and select a new Student Data Management System that aligns with CSUEB’s requirements.
Data Migration Planning: Develop a detailed plan for transferring data from the old system to the new system.
Implementation and Training: Roll out the new system and provide training sessions for admissions staff.
Pilot Testing: Test the new system with a small group of users to identify and resolve any issues before full implementation.
Full Implementation: Deploy the new system across the admissions department and retire the old system.
Justification
Migrating to a new Student Data Management System is crucial for CSUEB to enhance the efficiency and effectiveness of its admissions process. The existing system has proven to be inadequate in handling the increasing volume of applications and meeting compliance standards. By transitioning to a more advanced solution, CSUEB will be able to streamline operations, improve data accuracy, and provide a better experience for both staff and prospective students.

## WBS_Scope_Final
WBS 0 | WBS Level | Activity ID | Activity Description | Immediate Predecessor | Time (Weeks) | Other Details
| Project Initiation | 1 | Define Project Goals & Objectives | None | 0.5 | Must be completed first, sets project direction.
|  | 2 | Conduct Kick-off Meeting | 1 | 0.5 | Aligns all stakeholders and defines initial scope.
|  | 3 | Identify Stakeholders | 1 | 0.5 | Document key internal and external stakeholders.
| Needs Assessment | 4 | Conduct Interviews and Surveys | 3 | 1 | Gather data from departments using current systems.
|  | 5 | Compile System Requirements | 3 | 1 | Consolidate needs and capacity for the new system.
| System Design | 6 | Define Infrastructure Requirements | 5 | 1 | Specify hardware, software, and network needs.
|  | 7 | Create System Specifications | 5 | 1 | Detailed specs for server, storage, and network.
CSUEB - Data Migration
| Vendor Selection | 8 | Research Potential Vendors & RFPs | 7 | 1 | Identify vendors for hardware and services.
|  | 9 | Evaluate Vendor Proposals | 8 | 1 | Review proposals based on performance, cost, etc.
|  | 10 | Finalize Vendor Contracts | 8 | 0.5 | Select vendor and finalize contract terms.
| Implementation & Testing | 11 | Infrastructure Setup | 10 | 2 | Install servers, storage, and configure network.
|  | 12 | Data Migration (ETL) | 10 | 2 | Migrate data using Extract, Transform, Load (ETL).
|  | 13 | Pilot Testing | 12 | 1 | Test limited data to ensure accuracy and security.
|  | 14 | Staff Training | 12 | 1 | Conduct training sessions for IT staff and users.
|  | 15 | End-to-End Testing | 13 | 1.5 | Test the entire system (performance, security, etc).
| Feedback, Risk Management & Closure | 16 | Collect User Feedback | 15 | 0.5 | Gather feedback from pilot testing.
|  | 17 | Final Implementation | 15 | 1.5 | Deploy system fully after successful testing.
|  | 18 | Post-Implementation Review | 17 | 0.5 | Evaluate system performance, gather final feedback.
|  | 19 | Risk Monitoring & Mitigation | Continuous | Ongoing | Ensure continuous risk monitoring during the project.
Project Timeline (12 Weeks Breakdown)
Weeks 1-4: |  | 2 Conduct Kick-off Meeting
Project Initiation (Task 1-3) | 1 Define Project Goals & Objectives
Needs Assessment (Task 4-5) |  | 3 Identify Stakeholders |  | 4 Conduct Interviews and Surveys
System Design (Task 6-7)
5 Compile System Requirements
Weeks 5-8:
Vendor Selection (Task 8-10) |  |  |  | 6 Define Infrastructure Requirements
Infrastructure Setup & Data Migration (Task 11-12)
7 Create System Specifications
Weeks 9-12:
Pilot Testing & Staff Training (Task 13-14) |  |  |  | 8 Research Potential Vendors
End-to-End Testing (Task 15)
Full Implementation (Task 17) |  |  |  | 9 Evaluate Vendor Proposals
Closure and Risk Management (Task 16, 18-19)
10 Finalize Vendor Contracts
11 Infrastructure Setup
[6 empty] | 13. Pilot Testing | 16 Collect User Feedback
12 Data Migration (ETL)
[6 empty] | 14 Staff Training | 15 End-to-End Testing | 17 Final Implementation | 18 Post-Implementation Review
19 Risk Monitoring & Mitigation

## Gant Chart
Given the network and cost estimates, develop the baseline budget for the project
|  |  |  | 2024-11-01 | [8 empty] | 2024-12-01 | [8 empty] | 2025-01-01
|  |  |  | Week 1 (Oct 28 - Nov 3) |  | Week 2 (Nov 4 - Nov 10) |  | Week 3 (Nov 11 - Nov 17) |  | Week 4 (Nov 18 - Nov 24) |  | Week 5 (Nov 25 - Dec 1) |  | Week 6 (Dec 2 - Dec 8) |  | Week 7 (Dec 9 - Dec 15) |  | Week 8 (Dec 16 - Dec 22) |  | Week 9 (Dec 23 - Dec29) |  | Week 10 (Dec 30 - Jan 5) |  | Week 11 (Jan 6 - Jan 12) |  | Week 12 (Jan 13 - Jan 19)
Activity # | Activity Title | Duration | Immediate Predecessor | First Half | Second Half | First Half | Second Half | First Half | Second Half | First Half | Second Half | First Half | Second Half | First Half | Second Half | First Half | Second Half | First Half | Second Half | First Half | Second Half | First Half | Second Half | First Half | Second Half | First Half | Second Half
1 | Define Project Goals & Objectives | 0.5 | None
2 | Conduct Kick-off Meeting | 0.5 | 1
3 | Identify Stakeholders | 0.5 | 1
4 | Conduct Interviews and Surveys | 1 | 3
5 | Compile System Requirements | 1 | 3
6 | Define Infrastructure Requirements | 1 | 5
7 | Create System Specifications | 1 | 5
8 | Research Potential Vendors | 1 | 7
9 | Evaluate Vendor Proposals | 1 | 8
10 | Finalize Vendor Contracts | 0.5 | 8
11 | Infrastructure Setup | 2 | 10
12 | Data Migration (ETL) | 2 | 10
13 | Pilot Testing | 1 | 12
14 | Staff Training | 1 | 12
15 | End-to-End Testing | 1.5 | 13
16 | Collect User Feedback | 0.5 | 15
17 | Final Implementation | 1.5 | 15
18 | Post-Implementation Review | 0.5 | 17
19 | Risk Monitoring & Mitigation | Ongoing | Continuous

## WBS_Skeleton
LEVEL 0 |  |  | CSUEB Data Migration - Student Academic Center
| TASK ID |  |  |  |  | Work Breakdown Structure (WBS)
LEVEL 1 |  | Project Initiation: |  |  | Needs Assessment: |  | System Design: |  | Vendor Selection: |  |  | Implementation and Testing:
|  | Define Project Goals & Objectives |  | Identify stakeholders | Conduct interviews and surveys | Compile system requirements | Define infrastructure requirements | Create system specifications | Research potential vendors | Evaluate vendor proposals | Infrastructure Setup | Data Migration | Testing | Feedback, Risk Management & Closure
LEVEL 2 |  | Conducting Kick-off Meeting |  | Identify and document key internal and external stakeholders | Identify departments/units using current server systems | Analyze existing system’s data storage and performance issues | Analyze hardware and software specifications for the new server | Create detailed infrastructure design diagrams (server, storage, network) | Identify potential vendors for hardware, software, and services | Review and evaluate vendor proposals based on selection criteria | Procure necessary hardware and software licenses | Create detailed data migration plan (mapping and sequencing) | Create a training curriculum for IT staff and end-users | Identify departments for pilot testing | Collect feedback from pilot users
|  | Define project scope, deliverables, and success criteria |  | Conduct stakeholder analysis | Schedule and conduct interviews with key system users and administrators | Compile user needs and future capacity requirements | Define data storage and backup solutions | Define data migration architecture and transfer protocols |  | Conduct vendor demonstrations or Proof of Concept (PoC) | Install physical or cloud-based servers and storage | Extract, Transform, Load (ETL) of data into new system | Conduct hands-on and virtual training sessions | Migrate limited data for testing purposes | Resolve issues from the feedback and retest
|  | Document project charter |  | Define stakeholder communication plan | Design and distribute surveys to collect broader feedback | Identify data security, compliance, and accessibility requirements | Ensure network bandwidth, server scalability, and redundancy requirements | Develop high-level and low-level design documentation |  | Score and rank vendors | Configure network and security settings | Validate data integrity and ensure no data loss | Develop training documentation and user manuals | Conduct end-to-end tests (security, performance, data accuracy) | Obtain user acceptance sign-off
|  | Set timeline, milestones, and critical path |  | Set up regular meetings with stakeholders |  | Develop and finalize the system requirement documentation | Address cybersecurity infrastructure needs (firewalls, encryption) | Review system specifications with stakeholders and technical teams |  | Present vendor selection to stakeholders and finalize the contract | Set up disaster recovery and backup plans | Test performance post-migration (speed, accuracy, security) | Evaluate staff proficiency and address learning gaps | Document issues and iterate solutions